## Bookztron App - RTM Docx
Project | Project Manager
Bookztron App | NA
Contact | Date
NA | 18-03-2024
[6 empty] | Pass/Fail | number | Open / Close/ NA
Sr no | Request Id | Request Description | Scenario | Test Case Id | Test Case Description | Test Result | Defect Id | Defect Status
1 | BR 1.0 | there should be 5 navigation menu options brandloggo, wishlist, cart, shop, login after clicking on brand loggo should redirect to home page, after clicking on wishlist link should redirect to wishlist page, after clicking on cart link should redirect to cart page, after clicking on shop link should redirect to shop page, after clicking on login button should redirect to signin page | Header | TC_01 to TC_10 | Bookztron is an web platform which allows user to buy books of their choice,Navigation menu allows user to redirect to other web page. | Pass
2 | BR 1.1 | there should be footer links, where social footer links should be functional and redirect to correct page. | Footer | TC_01 to TC_08 | Bookztron is an web platform which allows user to buy books of their choice, footer social links allows user to redirect to know more details of page | Pass
3 | BR 1.2 | user should able to navigate to home page effectively, should able to see navigation menus, footer links, home page should display category and new arrival options after clicking on category option should redirect to shop page after clicking on new arrival option should redirect to book detail page. | Home page | TC_01 to TC_11 | Bookztron is an web platform which allows user to buy books of their choice, home page ensures user gets proper information and information what platform is serving | Fail | TC_11 | Open
4 | BR 1.3 | proper validation should be applied on fields for incorrect data, security should be present, proper alert should be displayed for validations, after successfully signup user should redirect to correct page | Signup | TC_01 to TC_25 | Bookztron is an web platform which allows user to buy books of their choice, Signup form should allow user to sign up with name, email, password and terms and condition checkbox, there should be validations applied on each field for incorrect data submission. | Fail | TC_07, TC_08, TC_09, TC_10, TC_11, TC_12, TC_13, TC_14, TC_15, TC_16,TC_17, TC_18, TC_19, TC_20, TC_21, TC_22, TC_23, TC_24 | Open
5 | BR 1.4 | proper validation should be applied on fields for incorrect data, security should be present, proper alert should be displayed for validations, after successfully signin user should redirect to correct page | Signin | TC_01 to TC_09 | Bookztron is an web platform which allows user to buy books of their choice, Signin form should allow user to signin with correct details (i.e., email address, password field), validations should be applied on fields for incorrect user input | Fail | TC_05, TC_06, TC_09 | Open
6 | BR 1.5 | user should able to see product list page, filters and search field should work properly, pagination should work properly, proper redirection should be applied. | Shop page | TC_01 to TC_58 | user should allow to select book according to their choice with correct filters ensure product counts are correct for different filters like category, price, rating, sort by, ensure wishlist icon is functional | Fail | TC_08, TC_57, TC_58 | Open
7 | BR 1.6 | user should able to redirect book detail page after clicking on book option from list, on book detail page, there should be 2 button add to wishlist and add to cart both button should be functional, after click on wishlist button specific selected book item should be added to wishlist and wishlist count should increase to 1. if trying to add to cart without signin state should prompt for error toaster to signin in first and after click on add to cart with signin state should increase cart count to 1. | Book detail page | TC_01 to TC_07 | Bookztron is an web platform which allows user to buy books of their choice, book detail page displays information of product its name, price with wishlist and add to cart button. both buttons should be functional | Pass
8 | BR 1.7 | user should able to add products to wishlist with or without signin, user can remove item from wishlist, when there is no item into wishlist there should be single button available go to shop where after clicking on it, user should redirect to shop page. | Wishlist page |  | Bookztron is an web platform which allows user to buy books of their choice, wishlist page displays all items that are added as wishlist from shop page | Pass
9 | BR 1.8 | user should able to add multiple products to cart, apply coupon, should able to add product to wishlist, should able to do payment | Cart page | TC_12 | Bookztron is an web platform which allows user to buy books of their choice, user should able to add product to cart, apply coupon, should able to add product to wishlist, should able to do payment | Fail | TC_12 | Open